## Project Timeline
Online PPT
TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2014-07-20 | Project Start | 25 | 1
2014-07-24 | Design of Website : PSD | -20 | 1
2014-07-26 | PSD to HTML | 7 | 1
2014-07-29 | CSS | -10 | 1
2014-07-30 | Javascript | 15 | 1
2014-08-02 | Create Database | -15 | 1
2014-08-06 | Login Form | 7 | 1
2014-08-10 | Registration user CRUD | -15 | 1
2014-08-13 | Session Checker | 15 | 1
2014-08-15 | CRUD Category | -20 | 1
2014-08-23 | CRUD Price | 10 | 1
2014-08-28 | CRUD Reputation | -15 | 1
2014-09-03 | Search Developer | 20 | 1
2014-09-09 | Post Project | 10 | 1
2014-09-15 | View Project Standing | -10 | 1
2014-09-19 | Open To Bid | -20 | 1
2014-09-22 | Create Profile | 10 | 1
2014-09-25 | Find Jobs | -5 | 1
2014-09-29 | Bid to Project | 20 | 1
2014-10-03 | Build Profile | -20 | 1
2014-10-08 | Search Category | 15 | 1
2014-10-16 | Reports | 10 | 1
2014-10-17 | Review Functional Requirements | -10 | 1
2014-10-18 | Testing | 20 | 1
2014-10-19 | Project End | -20 | 1
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.